## Sheet1
Sprint 22.6
Sprint Effort |  |  |  | Known Activities per person |  |  |  | Sprint Events |  |  |  |  | Legends
Total Sprint Effort |  | 392.5 | 392.5 | Sprint Planning Meeting 1 |  |  | 0 | SPM1 | [5 empty] | SPM1, SPM2, Daily Meet
Improvement |  | 0 |  | Sprint Planning Meeting 2 |  |  | 2 | SPM2 | [5 empty] | Sprint Review
Planned Bugs/Support |  | 29 |  | Daily Standup |  |  | 10 | StandUp | [5 empty] | Sprint Retrospective
Unplanned Issues |  | 20 |  | Sprint Review |  |  | 2 | Review | [5 empty] | PBR Analysis
Training (Session per sprint) |  | 0 |  | Sprint Retrospective |  |  | 1.5 | Retro | [5 empty] | Bank Holiday
Product Backlog Refinement |  | 65 | 0 | Meetings |  |  | 0 | PBR | [5 empty] | Full Day holidays
Unplanned Support |  | 15 |  | Improv. bcklog refnmnt. mtng |  |  | 0 | [6 empty] | Training
DS Activites |  | 17 |  | Leave bucket (hours) |  |  | 0 | [6 empty] | Half day
PB Item |  | 246.5 |  | Knowledge Transfer |  |  | 0
|  |  |  | Total known Activities |  |  | 15.5
Hours/day | 8 | #days | 11 |  | Team Effort Availability Chart
| Role | Total | Effort |  | Tue, Aug 13 | Wed, Aug 14 | Thu, Aug 15 | Fri, Aug 16 | Mon, Aug 19 | Tue, Aug 20 | Wed, Aug 21 | Thu, Aug 22 | Fri, Aug 23 | Mon, Aug 26 | Tue, Aug 27
|  | Effort | Available
Chirag | TEAM | 50.5 | 40.4 | Delhi | 4 |  | 8 |  | 8 | [5 empty] | 4
Vani | TEAM | 50.5 | 20.2 | Delhi | 4 |  | 8 |  | 8 | [5 empty] | 4
Avani | TEAM | 36.5 | 29.2 | Delhi | 4 |  | 8 | 8 | 8 |  |  |  |  | 4 | 8
Vikas | TEAM | 43.5 | 34.8 | Delhi | 4 |  | 8 |  | 8 |  |  |  | 8 |  | 4
Abhishek | TEAM | 40.5 | 32.4 | Delhi | 8 |  | 8 |  | 8 |  |  |  |  | 8 | 4
Aniket S | TEAM | 43.5 | 34.8 | Delhi | 4 |  | 8 |  | 8 |  |  |  | 8 |  | 4
Manav | TEAM | 43.5 | 34.8 | Delhi | 4 |  | 8 |  | 8 |  |  |  | 8 |  | 4
Aniket | TEAM | 43.5 | 34.8 | Delhi | 4 |  | 8 |  | 8 | 8 |  |  |  |  | 4
Deepak | TEAM | 40.5 | 32.4 | Delhi | 4 |  | 8 | 8 | 8 | [5 empty] | 8
Total Available Capacity
Jira Id |  | Estimates #hrs
CORESDK-5750 | 5 | [5 empty] | Planned Bugs
CORESDK-5394 | 23 | [5 empty] | Issue | Estimate
CORESDK-5811 | 14 | [5 empty] | ATPWM-3824 | 6
CORESDK-5811 | 35 | [5 empty] | ANG-9632 | 12
Necessity Indicator | 6 | [5 empty] | IONWEBQA-2793 | 6
[7 empty] | IONWEBQA-3882 | 3
Accessibility | 55.1 | [5 empty] | IONWEBQA-3885 | 2
DBX | 45.5
Product Management | 36.5
MyPortal | 13.1
Total | 233.05
Remaining capacity/Delta |  | 13.5
Refinement
CORESDK-5771 | 15
CORESDK-5835 | 20
CORESDK-5769 | 20
CORESDK-5821 | 10
Refinement Total | 65 | [5 empty] | TOTAL | 29